Draft budget allocation for the production of HUMABOT.

HUMABOT: RM15,000 Production Budget Breakdown

I. Pre-Production & Development (RM 1,200)

| Category | Item | Allocation (RM) | Notes |
| --- | --- | --- | --- |
| Script & Legal | Permissions/Releases | 300 | Location agreements, music rights (basic royalty-free tracks). |
| Admin & Casting | Casting Calls, Printing | 200 | Scripts, storyboards, scheduling prints. |
| Insurance | Basic Public Liability | 700 | Essential for protecting equipment and locations (3 days). |
| Subtotal |  | 1,200 |  |

II. Production Crew & Labor (RM 6,000)

This section assumes a highly efficient, small team working on fixed day rates over the 3-day schedule. Food is budgeted separately.

| Role | Rate (RM/Day) | No. of Days | Allocation (RM) | Notes |
| --- | --- | --- | --- | --- |
| Director / Producer | 0 | 3 | 0 | Typically deferred or compensated via profit-share in a micro-budget. |
| Director of Photography (DOP) | 500 | 4 | 2,000 | Includes 1 prep day. Critical role for the thriller atmosphere. |
| Gaffer / Grip | 350 | 3 | 1,050 | Essential for controlling light and shadows. |
| Sound Recordist | 350 | 3 | 1,050 | Crucial for clear dialogue and atmosphere (gongs, pangkis). |
| Production Manager (PM) | 400 | 3 | 1,200 | Handles all logistics, budget tracking, and scheduling. |
| Make-up / Wardrobe / Art Assist | 233 | 3 | 700 | Hybrid role for SFX, costume changes, and art tasks. |
| Subtotal |  |  | 6,000 |  |

III. Talent & Cast (RM 2,500)

This section focuses on compensation for the main actors and specialized performers. Extras are paid a token fee/provided food only (budgeted under catering).

| Role | Rate (RM/Day) | No. of Days | Allocation (RM) | Notes |
| --- | --- | --- | --- | --- |
| BIBI (Lead) | 300 | 3 | 900 | Highest rate for the lead role. |
| RODI | 200 | 2 | 400 | Supporting role, needed for 2 days. |
| ADAM | 150 | 1 | 150 | Crucial final scene; only one main shoot day. |
| SINARI (Voice/Body Double) | 100 | 1 | 100 | Minimal on-set time, focus on voice recording/vision scenes. |
| Magunatip Dancers (2) | 150 | 1 | 300 | Specialized skill required for 1 day. |
| Other Minor Roles (Hana, Cursed Woman) | 150 | 2 | 300 | 2 minor roles, 1 day each. |
| Token for 20 Extras | 10 | 2 | 350 | RM10/day token for 20 people over 2 days. |
| Subtotal |  |  | 2,500 |  |

IV. Art Department, Props, & Wardrobe (RM 1,200)

Focus on buying unique, essential props and creating the special effects.

| Item | Allocation (RM) | Notes |
| --- | --- | --- |
| Red Umbrella | 100 | Purchase and slight modification for effects. |
| SFX Makeup / Prosthetics | 300 | Blood, tangkal, aging/possession effects. |
| Wardrobe/Costume Rental | 400 | Rental of authentic Magunatip costumes for Bibi and dancers. |
| Set Dressing / Art Supplies | 400 | Trophies (cheap replicas), photos, general dressing for Bibi's room and village. |
| Subtotal |  | 1,200 |

V. Equipment, Logistics, & Accommodations (RM 2,800)

This assumes renting a basic camera package and borrowing/renting a small lighting kit. Using crew vehicles for transport.

| Item | Allocation (RM) | Notes |
| --- | --- | --- |
| Camera & Lens Rental | 1,000 | 3-day rental for a basic cinema camera and lenses (e.g., GH5/A7S package). |
| Basic Lighting & Grip Rental | 500 | Simple 2-3 point LED kit, stands, flags (essential for the thriller mood). |
| Location Fees | 500 | Small token fee for the Gelanggang Tarian and one internal location (e.g., Rumah Panjang/Dewan). |
| Fuel & Transport | 400 | Mileage/petrol for transport of gear and minimal crew movements. |
| Accommodation | 400 | Only for essential out-of-town crew (e.g., DOP, Sound) for 2 nights near the main location. |
| Subtotal |  | 2,800 |

VI. Catering & Craft Services (RM 800)

Essential for keeping the crew and cast energized and happy over the 3 days.

| Item | Allocation (RM) | Notes |
| --- | --- | --- |
| Catering | 800 | Lunch/Dinner for core crew (8-10 people) + snacks/drinks over 3 days. (Approx RM25 per person per meal). |
| Subtotal |  | 800 |

VII. Post-Production & Contingency (RM 500)

| Item | Allocation (RM) | Notes |
| --- | --- | --- |
| Post-Production | 200 | Software licensing fees, hard drive space. Editing and color grading are typically done by the director/DOP/an intern for this budget level. |
| Contingency | 300 | Crucial buffer for unforeseen issues (e.g., weather delay, broken prop, sudden permit cost). |
| Subtotal |  | 500 |

GRAND TOTAL

| Category | Budget Allocation (RM) |
| --- | --- |
| I. Pre-Production | 1,200 |
| II. Crew & Labor | 6,000 |
| III. Talent & Cast | 2,500 |
| IV. Art & Props | 1,200 |
| V. Equipment & Logistics | 2,800 |
| VI. Catering | 800 |
| VII. Post-Production & Contingency | 500 |
| TOTAL | RM 15,000 |